## STD load_NPI & EWF
G
[6 empty] | Task | 2 | 5 | 0 | 10 | 4 | 0 | 3 | 18 | 0 | 0 | 0 | 20 | 62 | D | 0.75 | 1.0625 | 0 | 4 | 1.5 | 0 | 1.75 | 8.75 | 0 | 8 | 0 | 9 | 34.8125
[20 empty] | H | 6 | 8.5 | 0 | 32 | 12 | 0 | 14 | 70 | 0 | 64 | 0 | 72 | 278.5
[7 empty] | PC | PLP | PCM | PMP | PQE | SQD | CAD | LPE | PPE | LAB | KAM | PM |  |  | PC | PLP | PCM | PMP | PQE | SQD | CAD | LPE | PPE | LAB | KAM | PM
|  | TYPE G |  |  | -
-
1 |  | 10 Requirements |  |  | PM | [26 empty] | 4 | bar: PM
2 |  |  | 10 Check internal order number |  | PM | [26 empty] | 4 | bar: PM
3 |  |  | 20 Check and complete Product datasheet |  | PM | [26 empty] | 4 | bar: PM
4 |  |  | 30 Create and define printing & packaging layout |  | PM | [26 empty] | 4 | bar: PM
5 |  |  | 40 Kick-off |  | PM | [26 empty] | 4 | bar: PM
6 |  |  | 60 Target costing |  | PC | [15 empty] | 4 | bar: PC
7 |  |  | 70 Pre-evaluation (for Chinese locations) |  | PM | [26 empty] | 4 | bar: PM
8 |  | 20 Cost & quotation |  |  | PM | [26 empty] | 4 | bar: PM
9 |  |  | 5 Create sample part number |  | LPE | [22 empty] | 2 | bar: LPE
10 |  |  | 10 Create RFQ input file |  | PMP | [18 empty] | 2 | bar: PMP
11 |  |  | 20 Send out RFQ |  | PMP | [18 empty] | 2 | bar: PMP
12 |  |  | 30 Receipt and processing of RFQ |  | PMP | [18 empty] | 2 | bar: PMP
13 |  |  | 40 Request supplier documents |  | PMP | [18 empty] | 4 | bar: PMP
14 |  |  | 50 Request PPAP and Packaging Data Sheet (PDS) |  | PMP | [18 empty] | 2 | bar: PMP
15 |  |  | 60 Receive, check and store supplier documents |  | LPE | [22 empty] | 2 | bar: LPE
16 |  |  |  | Product drawing (dxf + pdf) | LPE | [22 empty] | 2 | bar: LPE
17 |  |  |  | OE/2nd Tier confirmation (pdf) | PMP | [18 empty] | 4 | bar: PMP
18 |  |  |  | Diecut drawing (pdf, eps, ai or illustrator) or diecut dimenstions incl. PAP symbol | LPE | [22 empty] | 2 | bar: LPE
19 |  |  |  | TDS (xlsx) | LPE | [22 empty] | 2 | bar: LPE
20 |  |  | 70 Check/evaluate supplier technical datasheet | Supplier technical datasheet according requirements? | LPE | [22 empty] | 2 | bar: LPE
21 |  |  | 80 Order/Handover OE products / competitor products + accessories |  | PM | [26 empty] | 4 | bar: PM
22 |  |  |  | OE/ competitor products available? | PM | [26 empty] | 4 | bar: PM
23 |  |  |  | Accessories available? | PM | [26 empty] | 4 | bar: PM
24 |  |  | 90 Request parts from supplier (if required) |  | LPE | [22 empty] | 2 | bar: LPE
25 |  |  | 100 Receipt of samples (if required) |  | LPE | [22 empty] | 2 | bar: LPE
26 |  |  | 110 Visual inspection (if required) | Are forwarded parts visually OK or n.OK? | PM | [22 empty] | 4 |  |  |  | 4 | bar: PM
27 |  |  | 120 Evaluation, negotiation and selection of supplier |  | PMP | [18 empty] | 4 | bar: PMP
28 |  |  | 130 Execute sourcing decision |  | PMP | [18 empty] | 4 | bar: PMP
29 |  |  | 140 Supplier nomination |  | PMP | [18 empty] | 4 | bar: PMP
30 |  | 40 Sample evaluation |  |  | PM | [26 empty] | 4 | bar: PM
31 |  |  | 20 Mounting test part/s according requirement (if required) | Fitment confirmation in application required? | LPE | [22 empty] | 4 | bar: LPE
32 |  |  | 30 Initiate laboratory test and obtain due date (if required) | Check the possibility of reduce product validation by Family release, Supplier test bench validation, M+H nominated media, | LPE | [22 empty] | 4 | bar: LPE
33 |  |  | 40 Material tests acc. to requirements |  | LPE | [22 empty] | 4 | bar: LPE
34 |  |  |  | OE/competitor part tested | LAB | [24 empty] | 16
35 |  |  |  | Supplier part tested | LAB | [24 empty] | 16
36 |  |  | 50 Functional tests acc. to requirements |  | LPE | [22 empty] | 4 | bar: LPE
37 |  |  |  | OE/competitor part tested | LAB | [24 empty] | 16
38 |  |  |  | Supplier part tested | LAB | [24 empty] | 16
39 |  |  | 60 Create, release test report & propose improvements if failed | Functional release given? | LPE | [22 empty] | 8 | bar: LPE
40 |  |  | 71 Create, release measurement report for requested parts |  | PQE | [19 empty] | 2 | bar: PQE
41 |  |  | 80 Functional/Technical-release of supplier sample/product | Functional release given? | LPE | [22 empty] | 8 | bar: LPE
42 |  | 50 Serial BoM & drawing |  |  | PM | [26 empty] | 2 | bar: PM
43 |  |  | 20 Create item master |  | CAD | [21 empty] | 2 | bar: CAD
44 |  |  | 30 Create and internally release drawings |  | CAD | [21 empty] | 4 | bar: CAD
45 |  |  | 40 Release item master |  | CAD | [21 empty] | 4 | bar: CAD
46 |  |  | 50 Milestone 1: Item master released |  | PM | [26 empty] | 2 | bar: PM
47 |  |  | 60 Create and release technical datasheet |  | LPE | [22 empty] | 6 | bar: LPE
48 |  |  | 70 Create, release and store instruction manual |  | PM | [26 empty] | 2 | bar: PM
49 |  |  | 80 Request drawing approval from customer/supplier |  | PM | [26 empty] | 2 | bar: PM
50 |  |  | 90 Approve drawing (internal/external) |  | LPE | [22 empty] | 4 | bar: LPE
51 |  | 60 Packaging |  |  | PM | [26 empty] | 2 | bar: PM
52 |  |  | 50 Initiate / create folding box label / layout |  | LPE | [16 empty] | 2 |  |  |  |  | 2 | 4 |  |  |  | 4 | bar: LPE
53 |  |  | 80 Approve layout / label |  | LPE | [16 empty] | 4 |  |  |  |  | 2 | 4 |  |  |  | 4 | bar: LPE
54 |  | 70 Order finished goods |  |  | PM | [26 empty] | 2 | bar: PM
55 |  |  | 10 First order commitment |  | PMP | [18 empty] | 4 | bar: PMP
56 |  |  | 20 Release PPAP, Part Submission Warrant (PSW), Packaging Data Sheet (PDS) |  | PQE | [19 empty] | 2 | bar: PQE
57 |  |  | 30 Create SAP views |  | PLP | [16 empty] | 0.5 | bar: PLP
58 |  |  | 40 Create demands |  | PLP | [16 empty] | 0.5 | bar: PLP
59 |  |  | 50 Create MANN-FILTER demands |  | PLP | [16 empty] | 0.5 | bar: PLP
60 |  |  | 60 Execute order to supplier |  | PLP | [16 empty] | 0.5 | bar: PLP
61 |  |  | 70 Update confirmed delivery date in ERP |  | PLP | [16 empty] | 0.5 | bar: PLP
62 |  |  | 80 Finalize 1P1P |  | PC | [15 empty] | 2 | bar: PC
63 |  | 90 Product Release |  |  | PM | [26 empty] | 2 | bar: PM
64 |  |  | 10 Incoming good inspection | Incoming goods inspection done? | PQE | [19 empty] | 4 | bar: PQE
65 |  |  | 20 Milestone 2: Inform about parts on stock |  | PQE | [19 empty] | 4 | bar: PQE
66 |  |  | 30 Close NPI |  | PM | [26 empty] | 2 | bar: PM
-
blank | blank | blank | blank | blank | - | H
blank | blank | blank | blank | blank | - | Task | 0 | 11 | 0 | 1 | 8 | 0 | 3 | 5 | 2 | 0 | 0 | 18 | 48 | D | 0 | 3 | 0 | 0.5 | 3.25 | 0 | 6.5 | 7.5 | 5 | 5 | 0 | 7 | 37.75
blank | blank | blank | blank | blank | - | [14 empty] | H | 0 | 24 | 0 | 4 | 26 | 0 | 52 | 60 | 40 | 40 | 0 | 56 | 302
blank | blank | blank | blank | blank | - |  | PC | PLP | PCM | PMP | PQE | SQD | CAD | LPE | PPE | LAB | KAM | PM |  |  | PC | PLP | PCM | PMP | PQE | SQD | CAD | LPE | PPE | LAB | KAM | PM
|  | TYPE H |  |  | -
-
1 |  | 10 Requirements |  |  | PM | [26 empty] | 4 | bar: PM
2 |  |  | 10 Check and complete Product datasheet |  | PM | [26 empty] | 4 | bar: PM
3 |  |  | 20 Kick-off |  | PM | [26 empty] | 4 | bar: PM
4 |  |  |  | check internal order number | PM | [26 empty] | 4 | bar: PM
5 |  |  |  | clarify the need for samples | PM | [26 empty] | 4 | bar: PM
6 |  |  |  | check patent situation | LPE | [22 empty] | 8 | bar: LPE
7 |  |  |  | clarify necessary activities with purchasing | PM | [26 empty] | 4 | bar: PM
8 |  |  |  | update team | PM | [26 empty] | 4 | bar: PM
9 |  |  | 30 Check and complete team |  | PM | [26 empty] | 4 | bar: PM
10 |  | 70 Serial BoM & drawing |  |  | PM | [26 empty] | 4 | bar: PM
11 |  |  | 10 Create item master |  | CAD | [21 empty] | 8 | 4 | bar: CAD
12 |  |  | 20 Create and release drawings |  | CAD | [21 empty] | 40 | 4 | bar: CAD
13 |  |  | 30 Release item master |  | CAD | [21 empty] | 4 | 4 | bar: CAD
14 |  |  | 35 Milestone 1: Item master released |  | PM | [26 empty] | 4 | bar: PM
15 |  |  | 40 Create and release technical data sheet |  | LPE | [22 empty] | 8 | bar: LPE
16 |  |  | 60 Request drawing approval from customer/supplier |  | LPE | [22 empty] | 4 | bar: LPE
17 |  |  | 70 Approve drawing |  | LPE | [22 empty] | 4 | bar: LPE
18 |  | 80 Packaging |  |  | PM | [26 empty] | 2 | bar: PM
19 |  |  | 10 Define / update packaging data |  | PLP | [16 empty] | 3 | bar: PLP
20 |  |  | 20 Define packaging components |  | PLP | [16 empty] | 3 | bar: PLP
21 |  |  | 40 Plan packaging |  | PLP | [16 empty] | 2.5 | bar: PLP
22 |  |  | 50 Initiate/Create folding box label/layout |  | PLP | [16 empty] | 2 | [5 empty] | 4 | bar: PLP
23 |  |  | 70 Request layout / label approval from customer |  | PM | [26 empty] | 2 | bar: PM
24 |  |  | 80 Approve layout / label |  | PLP | [16 empty] | 2 | [5 empty] | 4 | bar: PLP
25 |  | 90 Plant preparation |  |  | PM | [26 empty] | 2 | bar: PM
26 |  |  | 10 Initiate POP |  | PPE | [23 empty] | 20 | bar: PPE
27 |  |  | 20 Confirm readiness for production |  | PPE | [23 empty] | 20 | bar: PPE
28 |  |  | 30 Check MDG (for Speyer only) |  | PLP | [16 empty] | 0.5 | bar: PLP
29 |  | 100 Order finished goods |  |  | PM | [16 empty] | 0.5 | [9 empty] | 2 | bar: PM
30 |  |  | 10 Create sales data in ERP |  | PLP | [16 empty] | 0.5 | bar: PLP
31 |  |  | 20 Create demands |  | PLP | [16 empty] | 0.5 | bar: PLP
32 |  | 110 Order production material |  |  | PM | [26 empty] | 2 | bar: PM
33 |  |  | 20 Set production order / Generate requirements for purchase orders |  | PLP | [16 empty] | 0.5 | bar: PLP
34 |  |  | 30 Procure production components |  | PMP | [18 empty] | 4 | bar: PMP
35 |  |  | 60 Manufacture parts and book into quarantine store |  | PLP | [16 empty] | 5 | bar: PLP
36 |  |  | 70 Milestone 2: Parts manufactured |  | PM | [26 empty] | 2 | bar: PM
37 |  | 120 Product Release |  |  | PM | [26 empty] | 2 | bar: PM
38 |  |  | 10 Create (internal) product quality release |  | PQE | [19 empty] | 2 | bar: PQE
39 |  |  | 20 Confirm sampling requirements |  | PQE | [19 empty] | 2 | bar: PQE
40 |  |  | 30 Create sampling documents |  | PQE | [19 empty] | 2 | bar: PQE
41 |  |  | 40 Optional: Request approval from customer |  | PQE | [19 empty] | 4 | bar: PQE
42 |  |  | 50 Approve samples |  | PQE | [19 empty] | 4 | bar: PQE
43 |  |  | 60 Optional: Forward to MR |  | PQE | [19 empty] | 4 | bar: PQE
44 |  |  | 70 Store released documents in CDB and inform "initiator" |  | PQE | [19 empty] | 4 | bar: PQE
45 |  |  | 130 Create test report & propose improvements if failed |  | LPE | [22 empty] | 16 |  | 40 | bar: LPE
46 |  |  | 150 Release parts from quarantine store and ship parts to central warehouse |  | PQE | [19 empty] | 4 | bar: PQE
47 |  |  | 160 Send out first shipment |  | PLP | [16 empty] | 4 | bar: PLP
48 |  |  | 200 Milestone 3: Close NPI |  | PM | [26 empty] | 2 | bar: PM
-
blank | blank | blank | blank | blank | - | I
blank | blank | blank | blank | blank | - | Task | 1 | 2 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 2 | 6 | 15 | D | 0.5 | 0.125 | 0 | 0 | 0 | 1.25 | 0.5 | 0.25 | 0 | 0 | 0.75 | 2.25 | 5.625
blank | blank | blank | blank | blank | - | [14 empty] | H | 4 | 1 | 0 | 0 | 0 | 10 | 4 | 2 | 0 | 0 | 6 | 18 | 45
blank | blank | blank | blank | blank | - |  | PC | PLP | PCM | PMP | PQE | SQD | CAD | LPE | PPE | LAB | KAM | PM |  |  | PC | PLP | PCM | PMP | PQE | SQD | CAD | LPE | PPE | LAB | KAM | PM
|  | TYPE I |  |  | -
-
1 |  | 10 Requirements |  |  | PM | [26 empty] | 4 | bar: PM
2 |  |  | 10 Check and complete Product datasheet |  | KAM | [25 empty] | 4 | bar: KAM
3 |  |  | 20 Check and complete team |  | PM | [26 empty] | 4 | bar: PM
4 |  | 30 Serial BoM & drawing |  |  | PM | [26 empty] | 4 | bar: PM
5 |  |  | 20 Create and release drawings |  | LPE | [21 empty] | 4 | 2 | bar: LPE
6 |  | 40 Order finished goods |  |  | PM | [26 empty] | 2 | bar: PM
7 |  |  | 10 Create sales data |  | KAM | [25 empty] | 2 | bar: KAM
8 |  |  | 20 Create demands |  | PLP | [16 empty] | 0.5 | bar: PLP
9 |  |  | 30 Create MANN-FILTER demands |  | PLP | [16 empty] | 0.5 | bar: PLP
10 |  |  | 40 Finalize 1P1P |  | PC | [15 empty] | 4 | bar: PC
11 |  | 50 Product Release |  |  | PM | [26 empty] | 2 | bar: PM
12 |  |  | 10 Incoming goods inspection |  | SQD | [20 empty] | 2 | bar: CAD
13 |  |  |  | Incoming goods inspection done? | SQD | [20 empty] | 4 | bar: CAD
14 |  |  |  | Goods released? | SQD | [20 empty] | 4 | bar: CAD
15 |  |  | 20 Milestone 3: Close NPI |  | PM | [26 empty] | 2 | bar: PM
-
blank | blank | blank | blank | blank | - | P
blank | blank | blank | blank | blank | - | Task | 3 | 14 | 0 | 0 | 8 | 0 | 8 | 24 | 6 | 0 | 0 | 25 | 88 | D | 3 | 6 | 0 | 0 | 8.5 | 1 | 9.5 | 27.5 | 9 | 10 | 0 | 23.5 | 98
blank | blank | blank | blank | blank | - | [14 empty] | H | 24 | 48 | 0 | 0 | 68 | 8 | 76 | 220 | 72 | 80 | 0 | 188 | 784
blank | blank | blank | blank | blank | - |  | PC | PLP | PCM | PMP | PQE | SQD | CAD | LPE | PPE | LAB | KAM | PM |  |  | PC | PLP | PCM | PMP | PQE | SQD | CAD | LPE | PPE | LAB | KAM | PM
|  | TYPE P |  |  | -
-
1 |  | 10 Requirements |  |  | PM | [26 empty] | 36 | bar: PM
2 |  |  | 10 Check and complete Product datasheet |  | PM | [26 empty] | 4 | bar: PM
3 |  |  | 20 Check and complete team |  | PM | [26 empty] | 8 | bar: PM
4 |  |  | 30 Check internal order number |  | PM | [26 empty] | 4 | bar: PM
5 |  |  | 40 Kick-off |  | PM | [26 empty] | 8 | bar: PM
6 |  |  | 50 Target costing |  | PC | [15 empty] | 8 | bar: PC
7 |  | 20 Performance evaluation |  |  | PM | [26 empty] | 4 | bar: PM
8 |  |  | 10 Order/Handover OE products / competitor products + accessories |  | PM | [26 empty] | 4 | bar: PM
9 |  |  | 40 Define test order and handover OE / competitor products to test laboratory |  | LPE | [22 empty] | 8 | bar: LPE
10 |  |  | 50 Test OE / competitor product (functional tests) |  | LPE | [24 empty] | 20 | bar: LPE
11 |  |  | 60 Test OE / competitor product (material) |  | LPE | [24 empty] | 20 | bar: LPE
12 |  |  | 70 Create and release test report & layout |  | LPE | [22 empty] | 16 | bar: LPE
13 |  | 30 Cost & quotation |  |  | PM | [26 empty] | 16 | bar: PM
14 |  |  | 20 Price request to plant controlling |  | PC | [15 empty] | 8 | bar: PC
15 |  | 40 Design concept |  |  | PM | [26 empty] | 4 | bar: PM
16 |  |  | 10 Create sample part number | Link created part number(s) to NPI-Project and confirm | LPE | [21 empty] | 4 | 8 | bar: LPE
17 |  |  | 20 Align design concept | Are MANN + HUMMEL patents connected with parts/products? | LPE | [22 empty] | 16 | bar: LPE
18 |  |  | 30 Check tooling ownership |  | PPE | [23 empty] | 12 | bar: PPE
19 |  |  | 40 Last call (stage 1) |  | PM | [26 empty] | 4 | bar: PM
20 |  |  | 50 Initiate evaluation patent situation |  | LPE | [22 empty] | 8 | bar: LPE
21 |  |  | 60 Patent research |  | LPE | [22 empty] | 8 | bar: LPE
22 |  |  | 70 Evaluate patent research |  | LPE | [22 empty] | 8 | bar: LPE
23 |  | 50 Sample production |  |  | PM | [26 empty] | 4 | bar: PM
24 |  |  | 10 Create sample order |  | LPE | [22 empty] | 4 | bar: LPE
25 |  |  | 20 Design samples and create drawings |  | LPE | [21 empty] | 12 | 8 | bar: LPE
26 |  |  |  | D-FMEA initiated | LPE | [22 empty] | 8 | bar: LPE
27 |  |  |  | Check existing/matching components (to avoid duplicates) | LPE | [22 empty] | 8 | bar: LPE
28 |  |  | 30 Order sample material |  | PPE | [23 empty] | 8 | bar: PPE
29 |  |  | 40 Produce sampling |  | PPE | [23 empty] | 16 | bar: PPE
30 |  | 60 Sample evaluation |  |  | PM | [26 empty] | 4 | bar: PM
31 |  |  | 30 Initiate laboratory test |  | LPE | [22 empty] | 8 | bar: LPE
32 |  |  | 40 Test sample product (functional test) |  | LPE | [24 empty] | 20 | bar: LPE
33 |  |  | 60 Create, release test report and propose improvements if failed (samples) |  | LPE | [22 empty] | 16 | bar: LPE
34 |  |  |  | Confirm mounting test | CAD | [21 empty] | 8 | bar: CAD
35 |  |  |  | Confirm mounting test | LPE | [22 empty] | 4 | bar: LPE
36 |  |  | 90 Last call (stage 2) |  | PM | [26 empty] | 8 | bar: PM
37 |  | 70 Serial BoM & drawing |  |  | PM | [26 empty] | 4 | bar: PM
38 |  |  | 10 Create item master | Link created part number(s) to NPI-Project and confirm | CAD | [21 empty] | 8 | bar: CAD
39 |  |  | 20 Create and release drawings |  | CAD | [21 empty] | 12 | bar: CAD
40 |  |  |  | D-FMEA up-to-date? | CAD | [21 empty] | 8 | bar: CAD
41 |  |  |  | Are MANN + HUMMEL patents connected with parts/products? | CAD | [21 empty] | 8 | bar: CAD
42 |  |  | 30 Milestone 1: Item master released |  | PM | [26 empty] | 4 | bar: PM
43 |  |  | 30 Release item master |  | CAD | [21 empty] | 4 | bar: CAD
44 |  |  | 40 Create and release technical datasheet |  | LPE | [21 empty] | 8 | 12 | bar: LPE
45 |  |  | 50 Create, release and store instruction manual |  | PM | [22 empty] | 16 |  |  |  | 4 | bar: PM
46 |  |  | 60 Request drawing approval from customer/supplier |  | PM | [22 empty] | 8 |  |  |  | 4 | bar: PM
47 |  |  | 70 Approval AZ-drawing (internal/external) |  | LPE | [22 empty] | 8 |  |  |  | 4 | bar: LPE
48 |  | 80 Packaging |  |  | PM | [26 empty] | 4 | bar: PM
49 |  |  | 10 Define / update packaging data |  | PLP | [16 empty] | 8 | bar: PLP
50 |  |  | 20 Define packaging components |  | PLP | [16 empty] | 8 | bar: PLP
51 |  |  | 40 Plan packaging |  | PLP | [16 empty] | 8 | bar: PLP
52 |  |  | 50 Initiate/create/release folding box / label-layout |  | PLP | [16 empty] | 8 | [5 empty] | 4 | bar: PLP
53 |  |  | 70 Request layout / label approval from customer |  | PM | [22 empty] | 4 |  |  |  | 8 | bar: PM
54 |  |  | 80 Approve layout / label |  | PLP | [16 empty] | 4 | bar: PLP
55 |  | 90 Plant preparation |  |  | PM | [26 empty] | 8 | bar: PM
56 |  |  | 20 Set-up production and confirm readiness |  | PPE | [23 empty] | 12 | bar: PPE
57 |  |  |  | P-FMEA documentation required and available? | PPE | [23 empty] | 12 | bar: PPE
58 |  |  |  | Confirm readiness for production | PPE | [23 empty] | 12 | bar: PPE
59 |  | 100 Order finished goods |  |  | PM | [26 empty] | 8 | bar: PM
60 |  |  | 10 Create sales data |  | PLP | [16 empty] | 0.5 | bar: PLP
61 |  |  | 20 Create demands |  | PLP | [16 empty] | 0.5 | bar: PLP
62 |  |  | 30 Create MANN-FILTER demands |  | PLP | [16 empty] | 0.5 | bar: PLP
63 |  | 110 Order production material |  |  | PM | [26 empty] | 8 | bar: PM
64 |  |  | 20 Set production order / Generate requirements for purchase orders |  | PLP | [16 empty] | 0.5 | bar: PLP
65 |  |  | 30 Procure production components |  | PLP | [16 empty] | 0.5 | bar: PLP
66 |  |  | 40 Order folding box |  | PLP | [16 empty] | 4 | bar: PLP
67 |  |  | 50 Confirm income of folding box |  | PLP | [16 empty] | 4 | bar: PLP
68 |  |  | 60 Manufacture parts and book into quarantine store |  | PLP | [16 empty] | 0.5 | bar: PLP
69 |  |  | 70 Finalize 1P1P |  | PC | [15 empty] | 8 | bar: PC
70 |  |  | 75 Milestone 2: Parts manufactured |  | PM | [26 empty] | 8 | bar: PM
71 |  | 120 Product Release |  |  | PM | [26 empty] | 8 | bar: PM
72 |  |  | 10 Create (internal) product quality release |  | PQE | [19 empty] | 8 | bar: PQE
73 |  |  |  | Quality documents available? | PQE | [19 empty] | 8 | bar: PQE
74 |  |  |  | Internal audit report available? | PQE | [19 empty] | 8 | bar: PQE
75 |  |  | 70 Store released documents in CDB and inform "initiator" |  | PQE | [19 empty] | 8 | bar: PQE
76 |  |  |  | P-FMEA and Control Plan (PLP) documentation required and available? | PQE | [19 empty] | 12 | bar: PQE
77 |  |  |  | Internal product release given? | PQE | [19 empty] | 8 | bar: PQE
78 |  |  |  | Optional: external product release (PPAP / PPF) given? | PQE | [19 empty] | 8 | bar: PQE
79 |  |  |  | Optional: product release for purchased parts (only if BOM with new purchased parts) given? | SQD | [20 empty] | 8 | bar: CAD
80 |  |  | 100 Initiate laboratory test |  | LPE | [22 empty] | 8 | bar: LPE
81 |  |  | 110 Test serial product (functional test) |  | LPE | [24 empty] | 20 | bar: LPE
82 |  |  | 130 Create, release test report & propose improvements if failed |  | LPE | [22 empty] | 16 | bar: LPE
83 |  |  |  | Confirm mounting test | LPE | [22 empty] | 8 | bar: LPE
84 |  |  |  | Confirm mounting test | CAD | [21 empty] | 4 | bar: CAD
85 |  |  |  | Functional release given? | LPE | [22 empty] | 8 | bar: LPE
86 |  |  | 150 Release parts from quarantine store and ship parts to central warehouse |  | PQE | [19 empty] | 8 | bar: PQE
87 |  |  | 170 Info about parts on stock |  | PLP | [16 empty] | 1 | bar: PLP
88 |  |  | 200 Milestone 3: Close NPI |  | PM | [26 empty] | 8 | bar: PM
[5 empty] | - | 156
blank | blank | blank | blank | blank | - | X
blank | blank | blank | blank | blank | - | Task | 0 | 11 | 0 | 1 | 11 | 0 | 4 | 2 | 3 | 0 | 1 | 16 | 49 | D | 0 | 3.1875 | 0 | 0.5 | 4.25 | 0.5 | 1.75 | 2.625 | 3.25 | 0 | 0.25 | 6.5 | 22.8125
blank | blank | blank | blank | blank | - | [14 empty] | H | 0 | 25.5 | 0 | 4 | 34 | 4 | 14 | 21 | 26 | 0 | 2 | 52 | 182.5
blank | blank | blank | blank | blank | - |  | PC | PLP | PCM | PMP | PQE | SQD | CAD | LPE | PPE | LAB | KAM | PM |  |  | PC | PLP | PCM | PMP | PQE | SQD | CAD | LPE | PPE | LAB | KAM | PM
|  | TYPE X |  |  | -
-
1 |  | 10 Requirements |  |  | PM | [26 empty] | 2 | bar: PM
2 |  |  | 20 Check tooling ownership |  | LPE | [22 empty] | 2 | 2 | bar: LPE
3 |  |  | 40 Check and complete Product datasheet |  | PM | [26 empty] | 2 | bar: PM
4 |  |  | 80 Define and align customer specific packaging details |  | PM | [26 empty] | 2 | bar: PM
5 |  |  | 90 Check and complete team |  | PM | [26 empty] | 2 | bar: PM
6 |  | 70 Serial BoM & drawing |  |  | PM | [26 empty] | 2 | bar: PM
7 |  |  | 10 Create item master |  | CAD | [21 empty] | 2 | bar: CAD
8 |  |  | 20 Create and release drawings | D-FMEA up-to-date? | CAD | [21 empty] | 8 | 4 | bar: CAD
9 |  |  | 30 Release item master |  | CAD | [21 empty] | 4 | 1 | bar: CAD
10 |  |  | 35 Milestone 1: Item master released |  | PM | [26 empty] | 4 | bar: PM
11 |  |  | 40 Create and release technical data sheet |  | LPE | [22 empty] | 6 | bar: LPE
12 |  |  | 60 Request drawing approval from customer/supplier |  | PM | [26 empty] | 4 | bar: PM
13 |  |  | 70 Approval AZ-drawing (internal/external) |  | PM | [26 empty] | 4 | bar: PM
14 |  | 80 Packaging |  |  | PM | [26 empty] | 4 | bar: PM
15 |  |  | 10 Define / update packaging data |  | PLP | [16 empty] | 6 | bar: PLP
16 |  |  | 20 Define packaging components |  | PLP | [16 empty] | 4 | bar: PLP
17 |  |  | 40 Plan packaging |  | PLP | [16 empty] | 6 | bar: PLP
18 |  |  | 50 Initiate/Create folding box label/layout |  | PLP | [16 empty] | 2 | [5 empty] | 4 | bar: PLP
19 |  |  | 70 Request layout / label approval from customer |  | PM | [26 empty] | 4 | bar: PM
20 |  |  | 80 Approve layout / label |  | PLP | [16 empty] | 2 | [5 empty] | 4 | bar: PLP
21 |  | 90 Plant preparation |  |  | PM | [26 empty] | 4 | bar: PM
22 |  |  | 20 Set-up production and confirm readiness |  | PPE | [23 empty] | 12 | bar: PPE
23 |  |  |  | P-FMEA documentation required and available? | PPE | [23 empty] | 8 | bar: PPE
24 |  |  |  | Confirm readiness for production | PPE | [23 empty] | 4 | bar: PPE
25 |  | 100 Order finished goods |  |  | PM | [26 empty] | 4 | bar: PM
26 |  |  | 10 Create sales data |  | PLP | [16 empty] | 0.5 | bar: PLP
27 |  |  | 30 Maintain customer price in SAP |  | KAM | [25 empty] | 2 | bar: KAM
28 |  |  | 40 Create demands |  | PLP | [16 empty] | 0.5 | bar: PLP
29 |  | 110 Order production material |  |  | PM | [26 empty] | 4 | bar: PM
30 |  |  | 20 Set production order / Generate requirements for purchase orders |  | PLP | [16 empty] | 0.5 | bar: PLP
31 |  |  | 30 Procure production components |  | PLP | [16 empty] | 0.5 | bar: PLP
32 |  |  | 40 Order folding box |  | PMP | [18 empty] | 4 | bar: PMP
33 |  |  | 50 Confirm income of folding box |  | PLP | [16 empty] | 3 | bar: PLP
34 |  |  | 60 Manufacture parts and book into quarantine store |  | PLP | [16 empty] | 0.5 | bar: PLP
35 |  |  | 75 Milestone 2: Parts manufactured |  | PM | [26 empty] | 4 | bar: PM
36 |  | 120 Product Release |  |  | PM | [26 empty] | 4 | bar: PM
37 |  |  | 10 Create (internal) product quality release |  | PQE | [19 empty] | 2 | bar: PQE
38 |  |  |  | Quality documents available? | PQE | [19 empty] | 2 | bar: PQE
39 |  |  |  | Internal audit report available? | PQE | [19 empty] | 2 | bar: PQE
40 |  |  | 20 Confirm sampling requirements |  | PQE | [19 empty] | 2 | bar: PQE
41 |  |  | 30 Create sampling documents |  | PQE | [19 empty] | 2 | bar: PQE
42 |  |  | 50 Approve samples |  | PQE | [19 empty] | 4 | bar: PQE
43 |  |  | 70 Store released documents in CDB and inform "initiator" |  | PQE | [19 empty] | 4 | bar: PQE
44 |  |  |  | P-FMEA and Control Plan (PLP) documentation required and available? | PQE | [19 empty] | 4 | bar: PQE
45 |  |  |  | Internal product release given? | PQE | [19 empty] | 4 | bar: PQE
46 |  |  |  | Optional: external product release (PPAP / PPF) given? | PQE | [19 empty] | 4 | bar: PQE
47 |  |  |  | Optional: product release for purchased parts (only if BOM with new purchased parts) given? | SQD | [20 empty] | 4 | bar: CAD
48 |  |  | 150 Release parts from quarantine store and ship parts to central warehouse |  | PQE | [19 empty] | 4 | bar: PQE
49 |  |  | 200 Close NPI |  | PM | [26 empty] | 2 | bar: PM
blank