## STD load_xSEP8
[8 empty] | Recursos | 1 | 1 | 2 | 2 | 1 | 1 | 2 | 6+2 | 4 | 3 | 7 | 2+1
[8 empty] | Total (T) | 11 | 8 | 0 | 61 | 37 | 2 | 8 | 49 | 69 | 5 | 20 | 43 | 313 | Total (D) | 11 | 12 | 0 | 89 | 52 | 8 | 72.5 | 102.25 | 240.75 | 53.75 | 25 | 55 | 721.25
[22 empty] | Total (H) | 88 | 96 | 0 | 712 | 416 | 64 | 580 | 818 | 1926 | 430 | 200 | 440 | 5770
[8 empty] | Task | 6 | 2 | 0 | 11 | 3 | 0 | 4 | 8 | 9 | 0 | 11 | 11 | 65 | D | 6 | 4.5 | 0 | 10.25 | 4.5 | 0 | 28 | 16.25 | 28 | 0 | 21.5 | 12.5 | 131.5
[22 empty] | H | 48 | 36 | 0 | 82 | 36 | 0 | 224 | 130 | 224 | 0 | 172 | 100 | 1052
[9 empty] | PC | PLP | PCM | PMP | PQE | SQD | CAD | LPE | PPE | LAB | KAM | PM |  |  | PC | PLP | PCM | PMP | PQE | SQD | CAD | LPE | PPE | LAB | KAM | PM
1 |  | 10 1. Quotation and Planning | 10 Request for Quote |  |  |  | KAM | [25 empty] | 24 | bar: KAM
2 |  | 10 1. Quotation and Planning | 20 Contract Review |  |  |  | KAM | [25 empty] | 24 | bar: KAM
3 |  | 10 1. Quotation and Planning | 30 Design Concept |  |  | Create Internal Order to track R&D cost | PM | [26 empty] | 2 | bar: PM
4 |  | 10 1. Quotation and Planning |  |  |  | Create R&D cost estimate | LPE | [22 empty] | 16 | bar: LPE
5 |  | 10 1. Quotation and Planning |  |  |  | Create 3D Models | CAD | [21 empty] | 48 | bar: CAD
6 |  | 10 1. Quotation and Planning |  |  |  | Create BOM | LPE | [22 empty] | 16 | bar: LPE
7 |  | 10 1. Quotation and Planning |  |  |  | Create DSR | LPE | [22 empty] | 6 | bar: LPE
8 |  | 10 1. Quotation and Planning |  |  |  | Create Initial Drawings | CAD | [21 empty] | 96 | bar: CAD
9 |  | 10 1. Quotation and Planning |  |  |  | Create DCR | LPE | [22 empty] | 16 | bar: LPE
10 |  | 10 1. Quotation and Planning |  |  |  | Design Concept Freeze | CAD | [21 empty] | 40 | bar: CAD
11 |  | 10 1. Quotation and Planning | 40 Quotation Preparation |  |  | Create PCR | PM | [26 empty] | 2 | bar: PM
12 |  | 10 1. Quotation and Planning |  |  |  | Create Technical Offer Presentation | LPE | [22 empty] | 16 | bar: LPE
13 |  | 10 1. Quotation and Planning |  |  |  | Create Volume Scenarios | KAM | [25 empty] | 2 | bar: KAM
14 |  | 10 1. Quotation and Planning |  |  |  | Make or Buy decision | PPE | [23 empty] | 16 | bar: PPE
15 |  | 10 1. Quotation and Planning |  |  |  | Estimation of purchased components | PMP | [18 empty] | 24 | bar: PMP
16 |  | 10 1. Quotation and Planning |  |  |  | Define Tooling Cost for Molds and Assembly Machines | PPE | [23 empty] | 80 | bar: PPE
17 |  | 10 1. Quotation and Planning |  |  |  | Define Directed Parts from the Customer | KAM | [25 empty] | 2 | bar: KAM
18 |  | 10 1. Quotation and Planning |  |  |  | Technical confirmation of in-house carryover components | PPE | [23 empty] | 8 | bar: PPE
19 |  | 10 1. Quotation and Planning |  |  |  | Technical confirmation of in-house carryover components | PQE | [19 empty] | 8 | bar: PQE
20 |  | 10 1. Quotation and Planning |  |  |  | Technical confirmation of purchased carryover components | PMP | [18 empty] | 8 | bar: PMP
21 |  | 10 1. Quotation and Planning |  |  |  | Create Process Flow Diagram | PPE | [23 empty] | 40 | bar: PPE
22 |  | 10 1. Quotation and Planning |  |  |  | Review Capacity and create initial investment estimate | PPE | [23 empty] | 12 | bar: PPE
23 |  | 10 1. Quotation and Planning |  |  |  | Define Packaging Concept | PLP | [16 empty] | 20 | bar: PLP
24 |  | 10 1. Quotation and Planning |  |  |  | Define Quality Control Means | PQE | [19 empty] | 8 | bar: PQE
25 |  | 10 1. Quotation and Planning |  |  |  | Calculate Product Standard Cost | PC | [15 empty] | 2 | bar: PC
26 |  | 10 1. Quotation and Planning |  |  |  | Create PER(s) | PC | [15 empty] | 32 | bar: PC
27 |  | 10 1. Quotation and Planning |  |  |  | PER approval Workflow | PC | [15 empty] | 2 | bar: PC
28 |  | 10 1. Quotation and Planning |  |  |  | Risk Analysis | PMP | [18 empty] | 8 | bar: PMP
29 |  | 10 1. Quotation and Planning |  |  |  | Feasibility Approval | PMP | [18 empty] | 2 | bar: PMP
30 |  | 10 1. Quotation and Planning |  |  |  | Project Timeline Creation | PMP | [18 empty] | 2 | bar: PMP
31 |  | 10 1. Quotation and Planning | 50 (MS) Submit Quotation |  |  | Create Quote Letter | KAM | [25 empty] | 16 | bar: KAM
32 |  | 10 1. Quotation and Planning |  |  |  | Quote approval | KAM | [25 empty] | 2 | bar: KAM
33 |  | 10 1. Quotation and Planning | 60 Quotation Review with Customer and refinement |  |  |  | KAM | [25 empty] | 80 | bar: KAM
34 |  | 10 1. Quotation and Planning | 70 (MS) Nomination |  |  |  | KAM | [25 empty] | 2 | bar: KAM
35 |  | 10 1. Quotation and Planning | 80 (MS) Project Kick Off |  |  |  | PM | [26 empty] | 2 | bar: PM
36 |  | 10 1. Quotation and Planning | 90 Gate 1 - Nomination and Planning Approval |  |  | Process Plan MP /Process Layout (PMC evaluation) | PPE | [23 empty] | 20 | bar: PPE
37 |  | 10 1. Quotation and Planning |  |  |  | Production Process Concept (PMC evaluation) | PPE | [23 empty] | 4 | bar: PPE
38 |  | 10 1. Quotation and Planning |  |  |  | Production Standard Overview /Planning (PMC evaluation) | PPE | [23 empty] | 4 | bar: PPE
39 |  | 10 1. Quotation and Planning |  |  |  | Planning, Preparation and Scoping of the P-FMEA (PMC evaluation) | PPE | [23 empty] | 40 | bar: PPE
40 |  | 10 1. Quotation and Planning |  |  |  | Packaging, Transportation, Logististics Concept, Supply Chain Checklist (PMC evaluation) | PLP | [16 empty] | 16 | bar: PLP
41 |  | 10 1. Quotation and Planning |  |  |  | Risk Assessment for Purchased Parts (PMC evaluation) | PMP | [18 empty] | 2 | bar: PMP
42 |  | 10 1. Quotation and Planning |  |  |  | pBOM updated and in line with PER (PMC evaluation) | PMP | [18 empty] | 16 | bar: PMP
43 |  | 10 1. Quotation and Planning |  |  |  | Carry-over Parts Check (Capacity & Tool Confirmation) (PMC evaluation) | PMP | [18 empty] | 2 | bar: PMP
44 |  | 10 1. Quotation and Planning |  |  |  | Kick-off Meeting after project nomination (PMC evaluation) | PMP | [18 empty] | 2 | bar: PMP
45 |  | 10 1. Quotation and Planning |  |  |  | Panel Sourcing List / PreRFQ (PMC evaluation) | PMP | [18 empty] | 8 | bar: PMP
46 |  | 10 1. Quotation and Planning |  |  |  | Sourcing Pipeline Planning (PMC evaluation) | PMP | [18 empty] | 8 | bar: PMP
47 |  | 10 1. Quotation and Planning |  |  |  | Planning, Preparation and Scoping of the D-FMEA (PMC evaluation) | LPE | [22 empty] | 16 | bar: LPE
48 |  | 10 1. Quotation and Planning |  |  |  | DSR (Spec./Product Assurance Plan)/ DVP (PMC evaluation) | LPE | [22 empty] | 32 | bar: LPE
49 |  | 10 1. Quotation and Planning |  |  |  | BOM, 3 D Model, Drawings (PMC evaluation) | LPE | [22 empty] | 12 | bar: LPE
50 |  | 10 1. Quotation and Planning |  |  |  | aPriori (cost evaluation based on CAD data) (PMC evaluation) | CAD | [21 empty] | 40 | bar: CAD
51 |  | 10 1. Quotation and Planning |  |  |  | Quality Planning Concept (PMC evaluation) | PQE | [19 empty] | 20 | bar: PQE
52 |  | 10 1. Quotation and Planning |  |  |  | Cost calculation incl. PER approval (PMC evaluation) | PC | [15 empty] | 2 | bar: PC
53 |  | 10 1. Quotation and Planning |  |  |  | Target Costing (PMC evaluation) | PC | [15 empty] | 2 | bar: PC
54 |  | 10 1. Quotation and Planning |  |  |  | Value Analysis/Value Engineering (PMC evaluation) | PC | [15 empty] | 8 | bar: PC
55 |  | 10 1. Quotation and Planning |  |  |  | PCR (PMC evaluation) | PM | [26 empty] | 2 | bar: PM
56 |  | 10 1. Quotation and Planning |  |  |  | Feasibility Confirmation (PMC evaluation) | PM | [26 empty] | 2 | bar: PM
57 |  | 10 1. Quotation and Planning |  |  |  | DLS Pre RFQ Report Out (PMC evaluation) | PM | [26 empty] | 16 | bar: PM
58 |  | 10 1. Quotation and Planning |  |  |  | DLS Offer Report Out (PMC evaluation) | PM | [26 empty] | 16 | bar: PM
59 |  | 10 1. Quotation and Planning |  |  |  | Timing Plan (PMC evaluation) | PM | [26 empty] | 40 | bar: PM
60 |  | 10 1. Quotation and Planning |  |  |  | Risk analysis (PMC evaluation) | PM | [26 empty] | 8 | bar: PM
61 |  | 10 1. Quotation and Planning |  |  |  | Kick-off/ Project Planning (PMC evaluation) | PM | [26 empty] | 8 | bar: PM
62 |  | 10 1. Quotation and Planning |  |  |  | Project Status Report (final PMC evaluation) | PM | [26 empty] | 2 | bar: PM
63 |  | 10 1. Quotation and Planning |  |  |  | Contract Compliance Sheet (PMC evaluation) | KAM | [25 empty] | 16 | bar: KAM
64 |  | 10 1. Quotation and Planning |  |  |  | Quotation incl. Approval (PMC evaluation) | KAM | [25 empty] | 2 | bar: KAM
65 |  | 10 1. Quotation and Planning |  |  |  | Customer Nomination (PMC evaluation) | KAM | [25 empty] | 2 | bar: KAM
blank | blank | blank | blank | blank | blank | blank | blank
blank | blank | blank | blank | blank | blank | blank | blank | Task | 0 | 2 | 0 | 4 | 4 | 0 | 1 | 19 | 0 | 2 | 3 | 7 | 42 | D | 0 | 4 | 0 | 6.25 | 3.25 | 0 | 26.5 | 42.875 | 0 | 10 | 1 | 21.5 | 115.375
blank | blank | blank | blank | blank | blank | blank | blank | [14 empty] | H | 0 | 32 | 0 | 50 | 26 | 0 | 212 | 343 | 0 | 80 | 8 | 172 | 923
blank | blank | blank | blank | blank | blank | blank | blank |  | PC | PLP | PCM | PMP | PQE | SQD | CAD | LPE | PPE | LAB | KAM | PM |  |  | PC | PLP | PCM | PMP | PQE | SQD | CAD | LPE | PPE | LAB | KAM | PM
66 |  | 20 2. Development | 20 Design Concept (BOM/3D/drawings) incl. CAE |  |  | Update RnD relevant documents | LPE | [22 empty] | 32 |  | 32 | bar: LPE
67 |  | 20 2. Development |  |  |  | Re-check specification for carryover parts | LPE | [22 empty] | 8 | bar: LPE
68 |  | 20 2. Development |  |  |  | Capex Initiation | LPE | [22 empty] | 4 | bar: LPE
69 |  | 20 2. Development | 30 Design Freeze - Prototype |  |  | 3D Models released | CAD | [21 empty] | 212 | bar: CAD
70 |  | 20 2. Development | 40 Prototype Order reception |  |  |  | KAM | [25 empty] | 4 | bar: KAM
71 |  | 20 2. Development | 50 Sourcing process for purchase parts (Prototypes) |  |  |  | PMP | [18 empty] | 4 | bar: PMP
72 |  | 20 2. Development | 60 (CP) Prototype Kick-off |  |  | Packaging, Transport, Logistics Concept, Supply Chain Checklist (CP evaluation) | PLP | [16 empty] | 16 | bar: PLP
73 |  | 20 2. Development |  |  |  | (update) Risk Assessment for Purchase Parts (CP evaluation) | PMP | [18 empty] | 2 | bar: PMP
74 |  | 20 2. Development |  |  |  | (update) pBOM (CP evaluation) | PMP | [18 empty] | 4 | bar: PMP
75 |  | 20 2. Development |  |  |  | sourcing process critical or early tooling kick-off tooling & PP (CP evaluation) | PMP | [18 empty] | 40 | bar: PMP
76 |  | 20 2. Development |  |  |  | Concept freeze with customer (CP evaluation) | LPE | [22 empty] | 24 | bar: LPE
77 |  | 20 2. Development |  |  |  | Feedback A-Prototype Customer Validation (CP evaluation) | LPE | [22 empty] | 8 | bar: LPE
78 |  | 20 2. Development |  |  |  | Test Report A-Prototypes (CP evaluation) | LPE | [22 empty] | 32 | bar: LPE
79 |  | 20 2. Development |  |  |  | Design Review A-Prototypes (CP evaluation) | LPE | [22 empty] | 8 | bar: LPE
80 |  | 20 2. Development |  |  |  | (update) DSR (Spec./Product Ass urance Plan)/ DVP (CP evaluation) | LPE | [22 empty] | 4 | bar: LPE
81 |  | 20 2. Development |  |  |  | A-/B- Prototype Manufacturing Plan (CP evaluation) | LPE | [22 empty] | 24 | bar: LPE
82 |  | 20 2. Development |  |  |  | 2D drawing agreement with customer (CP evaluation) | LPE | [22 empty] | 4 | bar: LPE
83 |  | 20 2. Development |  |  |  | RFQ Requirements for Nomination of tool suppliers and/ or Long Leadtime PU Parts (CP evaluation) | LPE | [22 empty] | 12 | bar: LPE
84 |  | 20 2. Development |  |  |  | (update) BOM, 3D data, drawings (CP evaluation) | LPE | [22 empty] | 10 | bar: LPE
85 |  | 20 2. Development |  |  |  | (update) D-FMEA documentation (CP evaluation) | LPE | [22 empty] | 16 | bar: LPE
86 |  | 20 2. Development |  |  |  | aPriori (cost evaluation based on CAD data) (PMC evaluation) | LPE | [22 empty] | 4 | bar: LPE
87 |  | 20 2. Development |  |  |  | Control Plan A-/B-Prototypes (CP evaluation) | PQE | [19 empty] | 6 | bar: PQE
88 |  | 20 2. Development |  |  |  | A-Prototype Inspection Report (CP evaluation) | PQE | [19 empty] | 6 | bar: PQE
89 |  | 20 2. Development |  |  |  | A-Prototype Part Release (CP evaluation) | PQE | [19 empty] | 6 | bar: PQE
90 |  | 20 2. Development |  |  |  | PCR (CR evaluation) | PM | [26 empty] | 2 | bar: PM
91 |  | 20 2. Development |  |  |  | (update) Feasibility Confirmation (CP evaluation) | PM | [26 empty] | 2 | bar: PM
92 |  | 20 2. Development |  |  |  | (update) Timing Plan (CP evaluation) | PM | [26 empty] | 40 | bar: PM
93 |  | 20 2. Development |  |  |  | (update) Risk Analysis (CP evaluation) | PM | [26 empty] | 2 | bar: PM
94 |  | 20 2. Development |  |  |  | Design Freeze Prototypes (CP evaluation) | PM | [26 empty] | 8 | bar: PM
95 |  | 20 2. Development |  |  |  | Project Status Report (CP evaluation) | PM | [26 empty] | 2 | bar: PM
96 |  | 20 2. Development |  |  |  | DLS Design Report out | PM | [26 empty] | 116 | bar: PM
97 |  | 20 2. Development |  |  |  | A-/B-Prototype customer specification (CP evaluation) | KAM | [25 empty] | 2 | bar: KAM
98 |  | 20 2. Development |  |  |  | Customer order A-/B-prototypes (CP evaluation) | KAM | [25 empty] | 2 | bar: KAM
99 |  | 20 2. Development | 70 Manufacture Prototype Tool build |  |  |  | LPE | [22 empty] | 16 | bar: LPE
100 |  | 20 2. Development | 80 Prototype Manufacturing |  |  |  | LPE | [22 empty] | 40 | bar: LPE
101 |  | 20 2. Development | 90 Prototype dimensional check |  |  |  | PQE | [19 empty] | 8 | bar: PQE
102 |  | 20 2. Development | 100 (MS) Prototype availability at customer |  |  |  | PLP | [16 empty] | 16 | bar: PLP
103 |  | 20 2. Development | 110 Prototype Validation (DVP) |  |  | Part Approval for Testing | LPE | [22 empty] | 1 |  | 40 | bar: LAB
104 |  | 20 2. Development |  |  |  | Testing completed | LPE | [22 empty] | 1 |  | 8 | bar: LAB
105 |  | 20 2. Development |  |  |  | Testing Report | LPE | [22 empty] | 50 | bar: LPE
106 |  | 20 2. Development |  |  |  | Customer approval of Testing Report | LPE | [22 empty] | 5 | bar: LPE
107 |  | 20 2. Development |  |  |  | Design Review | LPE | [22 empty] | 40 | bar: LPE
blank | blank | blank | blank | blank | blank | blank | blank
blank | blank | blank | blank | blank | blank | blank | blank | Task | 5 | 4 | 0 | 46 | 30 | 2 | 3 | 22 | 60 | 3 | 6 | 25 | 206 | D | 5 | 3.5 | 0 | 72.5 | 44.25 | 8 | 18 | 43.125 | 212.75 | 43.75 | 2.5 | 21 | 474.375
blank | blank | blank | blank | blank | blank | blank | blank | [14 empty] | H | 40 | 28 | 0 | 580 | 354 | 64 | 144 | 345 | 1702 | 350 | 20 | 168 | 3795
blank | blank | blank | blank | blank | blank | blank | blank |  | PC | PLP | PCM | PMP | PQE | SQD | CAD | LPE | PPE | LAB | KAM | PM |  |  | PC | PLP | PCM | PMP | PQE | SQD | CAD | LPE | PPE | LAB | KAM | PM
108 |  | 30 3. Industrialization | 10 Industrialization preparation |  |  |  | PM | [26 empty] | 8 | bar: PM
109 |  | 30 3. Industrialization | 20 Update Design for Mass Production |  |  | Re-check specification for carryover parts | LPE | [22 empty] | 4 | bar: LPE
110 |  | 30 3. Industrialization |  |  |  | Final decision for Make or Buy | PM | [26 empty] | 2 | bar: PM
111 |  | 30 3. Industrialization |  |  |  | Update R+D relevant documents | LPE | [22 empty] | 5 | bar: LPE
112 |  | 30 3. Industrialization | 30 Design Freeze Agreement |  |  | 3D Models and drawings released | LPE | [22 empty] | 36 | bar: LPE
113 |  | 30 3. Industrialization | 40 Customer Purchase Orders |  |  |  | KAM | [25 empty] | 2 | bar: KAM
114 |  | 30 3. Industrialization | 50 Tooling Sourcing for inhouse production parts |  |  | Drawing Released for Component | CAD | [21 empty] | 48 | bar: CAD
115 |  | 30 3. Industrialization |  |  |  | Tooling SOW | PPE | [23 empty] | 120 | bar: PPE
116 |  | 30 3. Industrialization |  |  |  | 3 Supplier Quotations | PMP | [18 empty] | 24 | bar: PMP
117 |  | 30 3. Industrialization |  |  |  | Sourcing Decision Sheet | PMP | [18 empty] | 8 | bar: PMP
118 |  | 30 3. Industrialization |  |  |  | Sourcing Board Approval | PMP | [18 empty] | 8 | bar: PMP
119 |  | 30 3. Industrialization | 60 Parts Sourcing |  |  | Drawing Released for Component | CAD | [21 empty] | 48 | bar: CAD
120 |  | 30 3. Industrialization |  |  |  | PRFPP signed by supplier | PMP | [18 empty] | 24 | bar: PMP
121 |  | 30 3. Industrialization |  |  |  | 3 Supplier Quotations | PMP | [18 empty] | 24 | bar: PMP
122 |  | 30 3. Industrialization |  |  |  | Sourcing Decision Sheet | PMP | [18 empty] | 8 | bar: PMP
123 |  | 30 3. Industrialization |  |  |  | Sourcing Board Approval | PMP | [18 empty] | 8 | bar: PMP
124 |  | 30 3. Industrialization | 70 Investment & Equipment Sourcing |  |  | Drawing Released for Assembly | CAD | [21 empty] | 48 | bar: CAD
125 |  | 30 3. Industrialization |  |  |  | Equipment SOW | PPE | [23 empty] | 120 | bar: PPE
126 |  | 30 3. Industrialization |  |  |  | 3 Supplier Quotations | PMP | [18 empty] | 24 | bar: PMP
127 |  | 30 3. Industrialization |  |  |  | CAPEX Preparation | PPE | [23 empty] | 40 | bar: PPE
128 |  | 30 3. Industrialization |  |  |  | Sourcing Decision Sheet | PMP | [18 empty] | 8 | bar: PMP
129 |  | 30 3. Industrialization |  |  |  | CAPEX Approval | PPE | [23 empty] | 8 | bar: PPE
130 |  | 30 3. Industrialization |  |  |  | Sourcing Board Approval | PMP | [18 empty] | 8 | bar: PMP
131 |  | 30 3. Industrialization | 80 Early Tooling Kickoff |  |  | Internal Part Design Freeze | LPE | [22 empty] | 6 | bar: LPE
132 |  | 30 3. Industrialization |  |  |  | Team Feasibility | PM | [26 empty] | 2 | bar: PM
133 |  | 30 3. Industrialization |  |  |  | PRFPP | PMP | [18 empty] | 8 | bar: PMP
134 |  | 30 3. Industrialization |  |  |  | Sourcing Decision Process | PMP | [18 empty] | 40 | bar: PMP
135 |  | 30 3. Industrialization |  |  |  | Purchase Order | PMP | [18 empty] | 24 | bar: PMP
136 |  | 30 3. Industrialization |  |  |  | Customer Information | KAM | [25 empty] | 4 | bar: KAM
137 |  | 30 3. Industrialization |  |  |  | Internal Processes | PM | [26 empty] | 2 | bar: PM
138 |  | 30 3. Industrialization |  |  |  | Risk Evaluation | PM | [26 empty] | 2 | bar: PM
139 |  | 30 3. Industrialization | 100 Gate 4 - Mass Production Kick-off Approval |  |  | (update) Packaging, Transport, Logistics Concept, Supply Chain Checklist (PMC evaluation) | PLP | [16 empty] | 6 | bar: PLP
140 |  | 30 3. Industrialization |  |  |  | (update) Production Process Concept (PMC evaluation) | PPE | [23 empty] | 40 | bar: PPE
141 |  | 30 3. Industrialization |  |  |  | Process Plan Mass Production /Process Layout (PMC evaluation) | PPE | [23 empty] | 8 | bar: PPE
142 |  | 30 3. Industrialization |  |  |  | P-FMEA documentation (PMC evaluation) | PPE | [23 empty] | 40 | bar: PPE
143 |  | 30 3. Industrialization |  |  |  | Capex Approval (PMC evaluation) | PPE | [23 empty] | 8 | bar: PPE
144 |  | 30 3. Industrialization |  |  |  | IPT preparation | PPE | [23 empty] | 40 | bar: PPE
145 |  | 30 3. Industrialization |  |  |  | HSE Risk Assessment | PPE | [23 empty] | 8 | bar: PPE
146 |  | 30 3. Industrialization |  |  |  | (update) Risk Assessment for Purchase Parts (PMC evaluation) | PMP | [18 empty] | 4 | bar: PMP
147 |  | 30 3. Industrialization |  |  |  | (update) pBOM (PMC evaluation) | PMP | [18 empty] | 4 | bar: PMP
148 |  | 30 3. Industrialization |  |  |  | PRFPP (PMC evaluation) | PMP | [18 empty] | 2 | bar: PMP
149 |  | 30 3. Industrialization |  |  |  | Sourcing decision (Sourcing Decision Sheet) (PMC evaluation) | PMP | [18 empty] | 2 | bar: PMP
150 |  | 30 3. Industrialization |  |  |  | Early kick off tooling for in house parts and/or PP (PMC evaluation) | PMP | [18 empty] | 24 | bar: PMP
151 |  | 30 3. Industrialization |  |  |  | Pre-series cost and quantity agreed (PMC evaluation) | PMP | [18 empty] | 8 | bar: PMP
152 |  | 30 3. Industrialization |  |  |  | eRFQ done (PMC evaluation) | PMP | [18 empty] | 8 | bar: PMP
153 |  | 30 3. Industrialization |  |  |  | Supplier Production Capacity Confirmation incl. carry-over parts (PMC evaluation) | PMP | [18 empty] | 8 | bar: PMP
154 |  | 30 3. Industrialization |  |  |  | Costed packaging data sheet (PDS) available (PMC evaluation) | PMP | [18 empty] | 8 | bar: PMP
155 |  | 30 3. Industrialization |  |  |  | Supplier Cost Break Down available (PMC evaluation) | PMP | [18 empty] | 4 | bar: PMP
156 |  | 30 3. Industrialization |  |  |  | APQP Overview available (PMC evaluation) | PMP | [18 empty] | 4 | bar: PMP
157 |  | 30 3. Industrialization |  |  |  | (update) OE Spare Parts (PMC evaluation) | LPE | [22 empty] | 4 | bar: LPE
158 |  | 30 3. Industrialization |  |  |  | Feedback Prototype Customer Validation (PMC evaluation) | LPE | [22 empty] | 6 | bar: LPE
159 |  | 30 3. Industrialization |  |  |  | Check concept & interfaces - Concept Freeze (PMC evaluation) | LPE | [22 empty] | 18 | bar: LPE
160 |  | 30 3. Industrialization |  |  |  | 2D drawing agereement with customer (PMC evaluation) | LPE | [22 empty] | 24 | bar: LPE
161 |  | 30 3. Industrialization |  |  |  | RFQ Requirements for Nomination of tool suppliers and or LL PP (PMC evaluation) | LPE | [22 empty] | 12 | bar: LPE
162 |  | 30 3. Industrialization |  |  |  | (update) DSR (Spec./Product Assurance Plan)/ DVP (PMC evaluation) | LPE | [22 empty] | 6 | bar: LPE
163 |  | 30 3. Industrialization |  |  |  | (update) BOM, 3D data, drawings (PMC evaluation) | LPE | [22 empty] | 6 | bar: LPE
164 |  | 30 3. Industrialization |  |  |  | (update) D-FMEA documentation (PMC evaluation) | LPE | [22 empty] | 12 | bar: LPE
165 |  | 30 3. Industrialization |  |  |  | Design Review B-Prototypes (PMC evaluation) | LPE | [22 empty] | 8 | bar: LPE
166 |  | 30 3. Industrialization |  |  |  | Perform DVP (validation plan)/Test Report B-prototypes (PMC evaluation) | LPE | [22 empty] | 24 |  | 80 | bar: LAB
167 |  | 30 3. Industrialization |  |  |  | Design Freeze Mass Production (PMC evaluation) | LPE | [22 empty] | 8 | bar: LPE
168 |  | 30 3. Industrialization |  |  |  | B Prototype Part Release (PMC evaluation) | PQE | [19 empty] | 8 | bar: PQE
169 |  | 30 3. Industrialization |  |  |  | SCL (PMC evaluation) | PQE | [19 empty] | 8 | bar: PQE
170 |  | 30 3. Industrialization |  |  |  | Control Plan Pre-and Series Production (PMC evaluation) | PQE | [19 empty] | 24 | bar: PQE
171 |  | 30 3. Industrialization |  |  |  | B Prototype Inspection Report (PMC evaluation) | PQE | [19 empty] | 2 | bar: PQE
172 |  | 30 3. Industrialization |  |  |  | Cost Calculation (M/P) + PER (PMC evaluation) | PC | [15 empty] | 8 | bar: PC
173 |  | 30 3. Industrialization |  |  |  | (update) Value Engineering/Value Analysis (PMC evaluation) | PC | [15 empty] | 8 | bar: PC
174 |  | 30 3. Industrialization |  |  |  | Customer order MP tooling (PMC evaluation) | KAM | [25 empty] | 2 | bar: KAM
175 |  | 30 3. Industrialization |  |  |  | (update) Feasibility Confirmation (PMC evaluation) | PM | [26 empty] | 2 | bar: PM
176 |  | 30 3. Industrialization |  |  |  | Pre-Production Planning (PMC evaluation) | PM | [26 empty] | 2 | bar: PM
177 |  | 30 3. Industrialization |  |  |  | (update) PCR (PMC evaluation) | PM | [26 empty] | 2 | bar: PM
178 |  | 30 3. Industrialization |  |  |  | DLS Production Preparation G4 Report Out (PMC evaluation) | PM | [26 empty] | 40 | bar: PM
179 |  | 30 3. Industrialization |  |  |  | (update) Timing Plan (PMC evaluation) | PM | [26 empty] | 8 | bar: PM
180 |  | 30 3. Industrialization |  |  |  | (update) Risk Analysis (PMC evaluation) | PM | [26 empty] | 2 | bar: PM
181 |  | 30 3. Industrialization |  |  |  | (update) Kick-Off/ Project Planning (PMC evaluation) | PM | [26 empty] | 8 | bar: PM
182 |  | 30 3. Industrialization |  |  |  | Project Status Report (PMC evaluation) | PM | [26 empty] | 2 | bar: PM
183 |  | 30 3. Industrialization | 110 Assembly (saleable product) |  |  |  | PM | [26 empty] | 2 | bar: PM
184 |  | 30 3. Industrialization |  | 10 Inhouse production component | 10 Tooling kick-off |  | LPE | [22 empty] | 2 | bar: LPE
185 |  | 30 3. Industrialization |  |  | 20 Tooling Development | Kickoff Meeting | PMP | [18 empty] | 16 | bar: PMP
186 |  | 30 3. Industrialization |  |  |  | Purchase Order | PMP | [18 empty] | 8 | bar: PMP
187 |  | 30 3. Industrialization |  |  |  | Interim Design Approval - OK to purchase Materials | PPE | [23 empty] | 8 | bar: PPE
188 |  | 30 3. Industrialization |  |  |  | Final Design Approval | PPE | [23 empty] | 8 | bar: PPE
189 |  | 30 3. Industrialization |  |  |  | Materials Ordered for Trials | PLP | [16 empty] | 16 | bar: PLP
190 |  | 30 3. Industrialization |  |  |  | First Shot Trial | PPE | [23 empty] | 8 | bar: PPE
191 |  | 30 3. Industrialization |  |  | 30 Tooling Refinement | Trial Run | PPE | [23 empty] | 24 | bar: PPE
192 |  | 30 3. Industrialization |  |  |  | Measurement of Samples | PQE | [19 empty] | 40 | bar: PQE
193 |  | 30 3. Industrialization |  |  |  | Samples Reviewed - Feedback Given to Supplier | PPE | [23 empty] | 24 | bar: PPE
194 |  | 30 3. Industrialization |  |  |  | Tuning Loop 1 | PPE | [23 empty] | 60 | bar: PPE
195 |  | 30 3. Industrialization |  |  |  | Trial Run | PPE | [23 empty] | 24 | bar: PPE
196 |  | 30 3. Industrialization |  |  |  | Measurement of Samples | PQE | [19 empty] | 8 | bar: PQE
197 |  | 30 3. Industrialization |  |  |  | Samples Reviewed - Feedback Given to Supplier | PPE | [23 empty] | 16 | bar: PPE
198 |  | 30 3. Industrialization |  |  |  | Tuning Loop 2 | PPE | [23 empty] | 60 | bar: PPE
199 |  | 30 3. Industrialization |  |  |  | Trial Run | PPE | [23 empty] | 24 | bar: PPE
200 |  | 30 3. Industrialization |  |  |  | Measurement of Samples | PQE | [19 empty] | 8 | bar: PQE
201 |  | 30 3. Industrialization |  |  |  | Tooling Acceptance at Vendor (OK to Ship) | PPE | [23 empty] | 16 | bar: PPE
202 |  | 30 3. Industrialization |  |  | 40 Tooling Shipment | Tooling Delivered to Production Site | PPE | [23 empty] | 24 | bar: PPE
203 |  | 30 3. Industrialization |  |  | 50 Tooling Release | Trial Run | PPE | [23 empty] | 24 | bar: PPE
204 |  | 30 3. Industrialization |  |  |  | Measurement of Samples | PQE | [19 empty] | 8 | bar: PQE
205 |  | 30 3. Industrialization |  |  |  | Samples Reviewed - Feedback Given to Supplier | PPE | [23 empty] | 16 | bar: PPE
206 |  | 30 3. Industrialization |  |  |  | Tuning Loop | PPE | [23 empty] | 60 | bar: PPE
207 |  | 30 3. Industrialization |  |  |  | Trial Run | PPE | [23 empty] | 24 | bar: PPE
208 |  | 30 3. Industrialization |  |  |  | Measurement of Samples | PQE | [19 empty] | 8 | bar: PQE
209 |  | 30 3. Industrialization |  |  |  | Tooling Acceptance at Production Site | PPE | [23 empty] | 8 | bar: PPE
210 |  | 30 3. Industrialization |  | 20 Purchased component | 10 Tooling Development | Kickoff Meeting | PMP | [18 empty] | 16 | bar: PMP
211 |  | 30 3. Industrialization |  |  |  | Purchase Order | PMP | [18 empty] | 8 | bar: PMP
212 |  | 30 3. Industrialization |  |  |  | First off tool parts | PMP | [18 empty] | 8 | bar: PMP
213 |  | 30 3. Industrialization |  |  | 20 (MS) FOT availability for purchased part(s) |  | PMP | [18 empty] | 8 | bar: PMP
214 |  | 30 3. Industrialization |  |  | 30 Tooling Refinement | Parts 100% Dimensional Status | PMP | [18 empty] | 8 | bar: PMP
215 |  | 30 3. Industrialization |  |  |  | Tooling Acceptance at tooling supplier | PMP | [18 empty] | 8 | bar: PMP
216 |  | 30 3. Industrialization |  |  | 40 Tooling Release | Samples Reviewed - Feedback Given to Supplier | PMP | [18 empty] | 8 | bar: PMP
217 |  | 30 3. Industrialization |  |  |  | Define Receiving Inspection | PMP | [18 empty] | 8 | bar: PMP
218 |  | 30 3. Industrialization |  |  |  | Run@Rate at supplier | PMP | [18 empty] | 40 | bar: PMP
219 |  | 30 3. Industrialization |  |  | 50 (MS) PPAP purchased part(s) approved |  | PMP | [18 empty] | 40 | bar: PMP
220 |  | 30 3. Industrialization |  | 30 Assembly equipment | 10 Equipment Development | Kickoff Meeting | PPE | [23 empty] | 24 | bar: PPE
221 |  | 30 3. Industrialization |  |  |  | Purchase Order | PMP | [18 empty] | 8 | bar: PMP
222 |  | 30 3. Industrialization |  |  |  | Interim Design Approval - OK to purchase Materials | PPE | [23 empty] | 40 | bar: PPE
223 |  | 30 3. Industrialization |  |  |  | Final Design Approval | PPE | [23 empty] | 40 | bar: PPE
224 |  | 30 3. Industrialization |  |  |  | Initial Runoff | PPE | [23 empty] | 24 | bar: PPE
225 |  | 30 3. Industrialization |  |  | 20 Equipment Refinement | Complete Machine Checklist | PPE | [23 empty] | 24 | bar: PPE
226 |  | 30 3. Industrialization |  |  |  | Initial Validation of part performance | PPE | [23 empty] | 120 | bar: PPE
227 |  | 30 3. Industrialization |  |  |  | Shipment of first samples | PPE | [23 empty] | 40 | bar: PPE
228 |  | 30 3. Industrialization |  |  |  | Measurement of Samples | PQE | [19 empty] | 8 | bar: PQE
229 |  | 30 3. Industrialization |  |  |  | Cycle Time Targets Achieved at Supplier | PPE | [23 empty] | 40 | bar: PPE
230 |  | 30 3. Industrialization |  |  |  | Tooling Acceptance at Vendor (OK to Ship) | PPE | [23 empty] | 16 | bar: PPE
231 |  | 30 3. Industrialization |  |  | 30 Equipment Shipment |  | PPE | [23 empty] | 40 | bar: PPE
232 |  | 30 3. Industrialization |  |  | 40 Equipment Release | Installation into the Production Plant | PPE | [23 empty] | 40 | bar: PPE
233 |  | 30 3. Industrialization |  |  |  | Create Initial Assemblies | PPE | [23 empty] | 40 | bar: PPE
234 |  | 30 3. Industrialization |  |  |  | Validation of part performance | PPE | [23 empty] | 40 | bar: PPE
235 |  | 30 3. Industrialization |  |  |  | Complete Machine Checklist | PPE | [23 empty] | 24 | bar: PPE
236 |  | 30 3. Industrialization |  |  |  | Measurement of Samples | PQE | [19 empty] | 8 | bar: PQE
237 |  | 30 3. Industrialization |  |  |  | Cycle Time Targets Achieved at Production site | PPE | [23 empty] | 24 | bar: PPE
238 |  | 30 3. Industrialization |  |  |  | Equipment Acceptance at Production Site | PPE | [23 empty] | 24 | bar: PPE
239 |  | 30 3. Industrialization |  | 40 Carry Over Components | 10 Update PPAP | Update PPAP for purchased carryover components | PMP | [18 empty] | 8 | bar: PMP
240 |  | 30 3. Industrialization |  |  |  | Update PPAP for in-house carryover components | SQD | [20 empty] | 24 | bar: SQD
241 |  | 30 3. Industrialization |  | 50 Assembly production & testing | 10 Product Validation Preparation |  | PM | [26 empty] | 2 | bar: PM
242 |  | 30 3. Industrialization |  |  | 20 (CP) Pre Production Readiness (PPT) | Effeciency | PPE | [23 empty] | 16 | bar: PPE
243 |  | 30 3. Industrialization |  |  |  | FTQ | PPE | [23 empty] | 16 | bar: PPE
244 |  | 30 3. Industrialization |  |  |  | Excel Checklist | PPE | [23 empty] | 8 | bar: PPE
245 |  | 30 3. Industrialization |  |  |  | PPT audit report | PQE | [19 empty] | 8 | bar: PQE
246 |  | 30 3. Industrialization |  |  | 30 First Customer Audit |  | PM | [26 empty] | 2 | bar: PM
247 |  | 30 3. Industrialization |  |  | 40 MP Parts dimensional check (assembly) |  | PQE | [19 empty] | 24 | bar: PQE
248 |  | 30 3. Industrialization |  |  | 50 M+H PV tests (Production Validation Tests) | Part Approval for Testing | LPE | [23 empty] | 40 | 40 | bar: LAB
249 |  | 30 3. Industrialization |  |  |  | Testing Completed | LPE | [23 empty] | 2 | 230 | bar: LAB
250 |  | 30 3. Industrialization |  |  |  | Testing Report | LPE | [22 empty] | 72 | bar: LPE
251 |  | 30 3. Industrialization |  |  |  | Customer Approval of Testing Report | LPE | [22 empty] | 8 | bar: LPE
252 |  | 30 3. Industrialization |  |  |  | Design Review | LPE | [22 empty] | 8 | bar: LPE
253 |  | 30 3. Industrialization |  |  | 60 (MS) Off Tool Parts availability at customer |  | PLP | [16 empty] | 2 | bar: PLP
254 |  | 30 3. Industrialization |  |  | 70 (CP) Production readiness (IPT) | Effeciency | PPE | [23 empty] | 16 | bar: PPE
255 |  | 30 3. Industrialization |  |  |  | FTQ | PPE | [23 empty] | 16 | bar: PPE
256 |  | 30 3. Industrialization |  |  |  | Excel Checklist | PPE | [23 empty] | 8 | bar: PPE
257 |  | 30 3. Industrialization |  |  |  | IPT audit report | PQE | [19 empty] | 8 | bar: PQE
258 |  | 30 3. Industrialization |  |  |  | PRFPP updated | PMP | [18 empty] | 8 | bar: PMP
259 |  | 30 3. Industrialization |  |  | 80 PPAP preparation |  | PQE | [19 empty] | 40 | bar: PQE
260 |  | 30 3. Industrialization |  |  | 90 (MS) Customer Run at Rate |  | PM | [26 empty] | 2 | bar: PM
261 |  | 30 3. Industrialization |  |  | 100 (MS) PPAP Submission |  | PQE | [19 empty] | 2 | bar: PQE
262 |  | 30 3. Industrialization |  |  | 110 PPAP customer review |  | PQE | [19 empty] | 2 | bar: PQE
263 |  | 30 3. Industrialization |  |  | 120 (MS) Customer PPAP Approval |  | PQE | [19 empty] | 8 | bar: PQE
264 |  | 30 3. Industrialization | 120 Gate 6 - SOP Kick-off Approval |  |  | Perequesites for invoicing (PMC evaluation) | PM | [26 empty] | 40 | bar: PM
265 |  | 30 3. Industrialization |  |  |  | update Timing Plan (PMC evaluation) | PM | [26 empty] | 8 | bar: PM
266 |  | 30 3. Industrialization |  |  |  | update Risk Analysis (PMC evaluation) | PM | [26 empty] | 2 | bar: PM
267 |  | 30 3. Industrialization |  |  |  | Project Status Report (PMC evaluation) | PM | [26 empty] | 2 | bar: PM
268 |  | 30 3. Industrialization |  |  |  | Invalidate Part No in CDB and disposition prototype tooling with customer (PMC evaluation) | KAM | [25 empty] | 2 | bar: KAM
269 |  | 30 3. Industrialization |  |  |  | Invoicing (PMC evaluation) | KAM | [25 empty] | 8 | bar: KAM
270 |  | 30 3. Industrialization |  |  |  | Customer Order - EDI (PMC evaluation) | KAM | [25 empty] | 2 | bar: KAM
271 |  | 30 3. Industrialization |  |  |  | Approved Tooling & Equipment Status (PMC evaluation) | PPE | [23 empty] | 8 | bar: PPE
272 |  | 30 3. Industrialization |  |  |  | Machine Capability (PMC evaluation) | PPE | [23 empty] | 8 | bar: PPE
273 |  | 30 3. Industrialization |  |  |  | Short Term Process Capability (PMC evaluation) | PPE | [23 empty] | 8 | bar: PPE
274 |  | 30 3. Industrialization |  |  |  | Production Standard Overview / Deployment (PMC evaluation) | PPE | [23 empty] | 8 | bar: PPE
275 |  | 30 3. Industrialization |  |  |  | Production Basics Document (PMC evaluation) | PPE | [23 empty] | 8 | bar: PPE
276 |  | 30 3. Industrialization |  |  |  | Tooling requirements for invoicing (PMC evaluation) | PPE | [23 empty] | 8 | bar: PPE
277 |  | 30 3. Industrialization |  |  |  | update P-FMEA Documentation (PMC evaluation) | PPE | [23 empty] | 40 | bar: PPE
278 |  | 30 3. Industrialization |  |  |  | update Process Plan Mass Production / Process Layout (PMC evaluation) | PPE | [23 empty] | 8 | bar: PPE
279 |  | 30 3. Industrialization |  |  |  | (Update) HSE Risk Assessment | PPE | [23 empty] | 8 | bar: PPE
280 |  | 30 3. Industrialization |  |  |  | update Packaging, Transport, Logistics Concept, Supply Chain Checklist (PMC evaluation) | PLP | [16 empty] | 4 | bar: PLP
281 |  | 30 3. Industrialization |  |  |  | PPAP release purchase parts (PMC evaluation) | PMP | [18 empty] | 8 | bar: PMP
282 |  | 30 3. Industrialization |  |  |  | update pBOM (PMC evaluation) | PMP | [18 empty] | 8 | bar: PMP
283 |  | 30 3. Industrialization |  |  |  | Tooling tag pictures available (PMC evaluation) | PMP | [18 empty] | 40 | bar: PMP
284 |  | 30 3. Industrialization |  |  |  | APQP overview updated (PMC evaluation) | PMP | [18 empty] | 8 | bar: PMP
285 |  | 30 3. Industrialization |  |  |  | Scheduling Agreement in place incl. agreed savings (LTA) (PMC evaluation) | PMP | [18 empty] | 8 | bar: PMP
286 |  | 30 3. Industrialization |  |  |  | Logistics Protocol available and handover to MP&L done (PMC evaluation) | PMP | [18 empty] | 8 | bar: PMP
287 |  | 30 3. Industrialization |  |  |  | Lessons Learned done (PMC evaluation) | PMP | [18 empty] | 8 | bar: PMP
288 |  | 30 3. Industrialization |  |  |  | DSR (Spec./Product Assurance Plan/ Requalification/FFAP) (PMC evaluation) | LPE | [22 empty] | 20 | bar: LPE
289 |  | 30 3. Industrialization |  |  |  | Perform Mass Production DVP/ Test Report Mass Production (PMC evaluation) | LPE | [22 empty] | 8 | bar: LPE
290 |  | 30 3. Industrialization |  |  |  | Design Review C (PMC evaluation) | LPE | [22 empty] | 8 | bar: LPE
291 |  | 30 3. Industrialization |  |  |  | update D-FMEA documentation (PMC evaluation) | LPE | [22 empty] | 40 | bar: LPE
292 |  | 30 3. Industrialization |  |  |  | C1/C2/C3 Prototype Inspection Report (PMC evaluation) | PQE | [19 empty] | 4 | bar: PQE
293 |  | 30 3. Industrialization |  |  |  | Mass Production Inspection Report (PMC evaluation) | PQE | [19 empty] | 4 | bar: PQE
294 |  | 30 3. Industrialization |  |  |  | C1/C2/C3 Prototype Part Release (PMC evaluation) | PQE | [19 empty] | 8 | bar: PQE
295 |  | 30 3. Industrialization |  |  |  | MSA (PMC evaluation) | PQE | [19 empty] | 40 | bar: PQE
296 |  | 30 3. Industrialization |  |  |  | Control Plan Pre-Series Production (PMC evaluation) | PQE | [19 empty] | 40 | bar: PQE
297 |  | 30 3. Industrialization |  |  |  | Material Declarations (PMC evaluation) | PQE | [19 empty] | 4 | bar: PQE
298 |  | 30 3. Industrialization |  |  |  | Control Plan Mass Production (PMC evaluation) | PQE | [19 empty] | 8 | bar: PQE
299 |  | 30 3. Industrialization |  |  |  | Tooling requirements for invoicing (PMC evaluation) | PQE | [19 empty] | 16 | bar: PQE
300 |  | 30 3. Industrialization |  |  |  | Internal Component Inspection Report (PMC evaluation) | SQD | [20 empty] | 40 | bar: SQD
301 |  | 30 3. Industrialization |  |  |  | PPAP preparation + Submission (PMC evaluation) | PQE | [19 empty] | 2 | bar: PQE
302 |  | 30 3. Industrialization |  |  |  | PPAP Approval (PMC evaluation) | PQE | [19 empty] | 2 | bar: PQE
303 |  | 30 3. Industrialization |  |  |  | update SCL (PMC evaluation) | PQE | [19 empty] | 2 | bar: PQE
304 |  | 30 3. Industrialization |  |  |  | SCL confirmation (PMC evaluation) | PQE | [19 empty] | 2 | bar: PQE
305 |  | 30 3. Industrialization |  |  |  | Capitalized Development cost (PMC evaluation) | PC | [15 empty] | 8 | bar: PC
306 |  | 30 3. Industrialization |  |  |  | update Cost calculation and PER update (PMC evaluation) | PC | [15 empty] | 8 | bar: PC
307 |  | 30 3. Industrialization | 130 (MS) Start Of Production (SOP) (Customer) |  |  |  | PM | [26 empty] | 2 | bar: PM
308 |  | 30 3. Industrialization | 140 (CP) Project Closure |  |  | Long-term process capability (CP evaluation) | PPE | [23 empty] | 8 | bar: PPE
309 |  | 30 3. Industrialization |  |  |  | Overall equipment efficiency - long term (CP evaluation) | PPE | [23 empty] | 8 | bar: PPE
310 |  | 30 3. Industrialization |  |  |  | Cost Calculation and PER update (CP evaluation) | PC | [15 empty] | 8 | bar: PC
311 |  | 30 3. Industrialization |  |  |  | Action plan from Risk Analysis executed (CP evaluation) | PM | [26 empty] | 8 | bar: PM
312 |  | 30 3. Industrialization |  |  |  | Project Status Report (CP evaluation) | PM | [26 empty] | 8 | bar: PM
313 |  | 30 3. Industrialization |  |  |  | Final Project Report (CP evaluation) | PM | [26 empty] | 8 | bar: PM